## Things to Note
Please see below for important notes regarding the Engagement Log
Operating Unit
Name of OU requesting support
Date of Request
Earliest date of unique request for support
Type of Request
Reverse TDY: | OU staff travel to ICPI for support on tools, country-specific needs, and/or trainings
TDY to Field: | ICPI staff travel to OU for support on tools, country-specific needs, and/or trainings
Virtual Support: | ICPI staff provide support from DC to OU for a variety of analytic needs and/or trainings; no travel included
Travel Dates
For Reverse TDY or TDY to the Field, travel dates to/from OU; *please specify whether proposed or actual dates
Requestor from OU
Name of POC from OU who initiated the request
HQ Gate Keeper
Name of POC from HQ who submitted/forwarded the request
Request Description
A few sentences describing the high-level request submitted
Request Decision by ICPI Leads
Approved: | Request was approved by ICPI Leads with no/minor changes to request
Denied: | Request was denied by ICPI Leads with no follow-up/referral to proceed
Referred: | Request is not appropriate for ICPI interagency support but was referred to another entity (i.e., agency-specific, data systems, etc.)
Date of Request Decision by ICPI Leads
Whether approved, denied, or referred, date of decision by ICPI Leads
Request Decision by ECT Management
Approved: | Request was approved by ECT Management with no/minor changes to request
Denied: | Request was denied by ECT Management with no follow-up/referral to proceed
Referred: | Request is not appropriate for ICPI interagency support but was referred to another entity (i.e., agency-specific, data systems, etc.)
Date of Request Decision by ECT Management
Whether approved, denied, or referred, date of decision by ECT Management
ICPI Analysts Involved?
Names of ICPI analysts who will support this request.
HQ POC
Name of POC at ICPI HQ who will be the primary liaison for the request
Current Status
New: | First unique request from OU; no support has been provided yet
Ongoing: | Request is being worked on and support is being currently provided
Completed: | Support for request has been provided and no follow-up actions remain
Withdrawn: | Request has been withdrawn (either by OU or by ICPI if rejected)
Most Recent Update/Notes
Most current updates relevant to the request; *please note the date next to each update, when possible
Immediate Next Steps
Next steps/ follow-up pending on request in order of priority
Due Date for Next Steps/Follow-Up
Date by which action items must be completed
Date Follow-Up Completed
Date action items/follow-up was completed
Link(s) to Output/Deliverable(s)
Sharepoint link to the various outputs (documents, tools, etc.) created through ICPI support

## ICPI Engagement Request Log
ICPI Engagement Log
Objective: | This log documents requests to assist in tracking ICPI engagement in order to provide comprehensive and collaborative support and communicate out successes and lessons learned.
Last updated: | 2018-02-07
By: | Kashmira Kale
Contact: | ICPI@state.gov
Operating Unit | Date of Request | Type of Request | Travel Dates (Reverse TDY/ TDY to Field only) | Requestor from OU | HQ Gate Keeper | Request Description | Request Decision by ICPI Leads | Date of Request Decision by ICPI Leads | ICPI Analyst(s) and *Other Collaborators Involved | HQ POC | Current Status | Most Recent Update/Notes | Immediate Next Steps and POC | Due Date for Next Steps/Follow-up | Date Follow-Up Completed | Link(s) to Output/Deliverable(s) | Contact Info
Zimbabwe | 1/18 | Virtual Support, TDY to Field | TBD | Vincent Wong, Lindsay Bonnano (via country team) |  | Support request in advance of their strategic retreat in January: identifying the appropriate testing strategies and how to cost them out. |  |  | Josh Davis, Jamie Houston, TBD | JP Abellera | New | - Engagement Form sent to ICPI | 1. Additional discussions hapenning to understand scope of engagement request 2. ICPI to send out standard email to relevant parties describing request status |  |  |  | JP Abellera (CDC) jla7@cdc.gov Josh Davis (USAID) jodavis@usaid.gov Vincent Wong vwong@usaid.gov Lindsay Bonnano BonannoLM@state.gov
South Sundan | 1/18 | Virtual Support | N/A | Tat'Yana Kenigsberg (SI Advisor South Sudan) |  | Merging some FactView datasets to create an accurate and comprehensive FactView for SS. Also to repopulate Datapack using the updated Factview file |  |  | Shazad Ahmed, Shaylee Mehta, Aaron Chafetz, Kristy Schlenker | Abe Agedew | Completed | Quick turnaround in resolving the issues. | No next steps |  |  |  | Tat'Yana K. Kenigsberg, ynf1@cdc.gov
Tanzania | 10/17 | TDY to Field | 12/4 - 12/13 | Request originally as a n agency-specific TDY but has been converted to interagency ECT-requested TDY |  | Orient TZ team to ICPI tools, with an emphasis on HITS, CHIPS, and C&T tools. Help with data triangulation with PHIA (if available), EA, and SIMS. Assist country team with understanding partner performance gaps and challenges as seen through the data. |  |  | Michelle Williams-Sherlock, Kashmira Kale, Imran Mujawar, *Ritu Pati, *Meena Srivastava, *Vincent Wong | Michelle Williams-Sherlock | Ongoing | - TDY completed; most objectives were met; follow up support will be required | 1. Provide TZ materials and virtual training to help team update TSD with Genie sitexIM extract 2. Provide virtual support for Tx_Net_New analyses 3. Folow-up on data automation (on hold until some vacant positions are filled) 4. Support ECT3 to develop ICPI support request for TZ visualizations and performance evaluations |  |  |  | Michelle Williams Sherlock (CDC) myy6@cdc.gov
Zambia | 10/2017 | Reverse TDY | 11/13/2017 - 11/17/2017 | Request from two separate Program tracks: Treatment: Minesh (HQ CDC) and Nzali (country team) MCH: Katie O'Connor and Annie (Country team) | Jamie Houston | Orientation to ICPI and to take lessons learned during the orientation to brainstorm analyses that can be used to address priorities identified during POART, for example, the Lusaka surge. | Approved | 2017-10-25 | Michelle Williams-Sherlock, Katie O'Connor | Kashmira Kale | Completed |  | Reverse TDY completed; Michelle WS and Katie O to follow-up if additional support is requested. |  |  |  | Michelle Williams Sherlock (CDC) myy6@cdc.gov Katie O'Connor (CDC) iyo6@cdc.gov
Ukraine | 10/04/2017 | TDY to Field | 07/18 | Bob Gern | Jamie Houston | 4-5 Day, 20 person QGIS training | Not Yet Reviewed |  | Gina Sarfaty backstopping as GIS WS lead; full GIS team will be engaged in support and review once SOW is developed. Victoria Ryan engaged as SI Advisor. | Zhanar Haimovich | Ongoing | GIS team and ICPI developed scope and updated training timeline | Training tentatively scheduled for July - ICPI to follow-up closer to time |  |  | https://www.pepfar.net/OGAC-HQ/icpi/Shared Documents/Forms/AllItems.aspx?RootFolder=%2FOGAC%2DHQ%2Ficpi%2FShared%20Documents%2FICPI%20Engagement%2FUkraine&FolderCTID=0x012000C815322C717A7E4B8164EA374FA254EC002682B939F9BED347BD49E43D77D3C691&View=%7B94C838B2%2DE166%2D4122%2DB8B4%2D7BEB9E1BC12B%7D | Gern, Robert W. (CDC/CGH/DGHT) icl4@cdc.gov Sarfaty, Gina M. (GH/OHA/SPER:CAMRIS) gsarfaty@usaid.gov
Ghana | 09/2017 | Virtual Support | N/A |  | Jamie Houston | Viral load scale-up (including GIS mapping of ART sites)? | Not Yet Reviewed |  | Jamie, JP, Abe | Anubhuti Mishra | New | Call with Ghana and ICPI took place on 10/4 to discuss support. | 1. Frank to share Ghana site coordinates 2. Frank to share extract from BLIS system for analysis 3. Erin to reach out to Joel and Dennis to inform of plan/get feedback 4. Jamie to f/u with Jasmine for additional interagency consensus | 1. 11/10/2017 2. 11/10/2017 3. TBD 4. TBD |  |  | Jamie Houston (CDC) vie3@cdc.gov JP Abellera (CDC) jla7@cdc.gov Abraham Agedew (CDC/ICF) lqe1@cdc.gov
Nigeria | 09/2017 | Reverse TDY | TBD | Otse Ogorry (SI Liaison) | Kristin Roha | To get better oriented with S/GAC & ICPI processes and the interagency SI role, to discuss use of updated population estimates (Gates-funded HH enumeration) for COP18 | Not Yet Reviewed |  | TBD | Jamie | Completed |  | Reverse TDY completed; Jamie to follow-up if additional support is requested.
Zimbabwe | 08/2017 | TBD | TBD | Shabeen & Parviez | Jamie and Josh??? | Multiple requests | Not Yet Reviewed |  | TBD | Kristine Clark | Withdrawn | Withdrawn after team received clarity on support types from the HQ side; does not need assistance from ICPI. | Request closed; Kristine will reach out in the future if have additional request. |  |  |  | Josh Davis (USAID) jodavis@usaid.gov
Rwanda | 06/2017 | Reverse TDY | 9/25/2017 - 9/29/2017 | Cheryl (PCO SI Advisor) | Leigh Tally | Reverse TDY to ICPI for use of MOH data to identify for hotspots for case finding | Approved | Mid August | Abe , Noah, *Parviez, Imran, Shazad, Michelle, Victoria | Leigh Tally | Completed | TDY completed and successful | 1. Nate/Abe to finalize maps (draft shared) 2. Abe working on resolving heirarchy issue in FACTview (for Q4) 3. Rwanda team reviewing and providing HITS/CHIPS/TSD feedback |  |  |  | Abe Agedew (ICF/CDC) lqe1@cdc.gov Noah Bartlett (USAID) nbartlett@usaid.gov Imran Mujawar (ICF/CDC) lrz5@cdc.govv Michelle Williams-Sherlock myy6@cdc.gov Victoria Ryan (USAID) vryan@usaid.gov
Kenya | 06/2017 | Reverse TDY | 06/2017 | Joe Barker | Jamie Houston | Reverse TDY to ICPI for understanding of bottlenecks in creation of analytic datasets | Approved | Late May | Kristy, Imran, Abe | Jamie Houston | Completed | Follow up discussions from reverse TDY were put on hold pending updates to data access through DATIM genie at Q4 | Jamie followed up with country team POC after Q4 but no response, can ask again in Joburg | TBD |  |  | Kristy Schlenker (USAID) kschlenker@usaid.gov Abraham Agedew (ICF/CDC) lqe1@cdc.gov Imran Mujawar (ICF/CDC) lrz5@cdc.gov
Uganda | 06/2017 | Reverse TDY, TDY to Field | 06/2017 (Reverse TDY) 10/2017 - 11/2017 (TDY) | Jen Galbraith (CDC Uganda) | Nadia Soledhin (CDC ATL) | Reverse TDY to ICPI for understanding of bottlenecks in creation of analytic datasets | Approved | Late May | Abe, Kristy, Imran, Shazad, and Yaa | Kristy S. | Ongoing | SOW for TDY to Uganda submitted (2 week Oct-Nov: Jamie, Kristy, Abe, Imran, and Jason K | TDY completed, next steps? | TBD |  |  | Kristy Schlenker (USAID) kschlenker@usaid.gov Abraham Agedew (ICF/CDC) lqe1@cdc.gov Imran Mujawar (ICF/CDC) lrz5@cdc.gov Shazad Ahmed (ICF/CDC) lqa9@cdc.gov Yaa Obeng-Aduasare (Peace Corps) yobengaduasare@peacecorps.gov
Mozambique | 05/2017 | TDY to Field | 05/2017, 07/2017 | POART team | Anna Radin | Transition from Dev Results to DATIM | Approved | May? | JP, Josh, Victoria, and Lindsay (CDC ATL) | Victoria Ryan | Ongoing? | Completed two TDYS, May and July. First on data entry the second on data quality review. What are the next steps on the wopper? | ??? |  |  |  | JP Abellera (CDC) jla7@cdc.gov Josh Davis (USAID) jodavis@usaid.gov Victoria Ryan (USAID) vryan@usaid.gov
Tanzania | 05/2017 | Virtual Support | N/A | Anike (DREAMS POC) | Katie I (DREAMS worksteam) | Site level Adol Friendly Services dash (DREAMS and HTS dashboard) | Approved | Mid August? | Katie I, Katya, Shazad (datset), Kimi (QC) | Kimi Sato | Ongoing? | DREAMS Site level dashboard - done - CLEARED and shared. HTS Dashboard cleared by leads. Draft created, plan for submission to clearance this week | Update both dashboards with clean Q4 data. No plans additional updates after that | 2017-01-16 |  | https://www.pepfar.net/OGAC-HQ/icpi/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FOGAC%2DHQ%2Ficpi%2FShared%20Documents%2FICPI%20Data%20Store%2FICPI%20Approved%20Tools%20%28most%20current%20version%29%2FDREAMS&FolderCTID=0x012000C815322C717A7E4B8164EA374FA254EC002682B939F9BED347BD49E43D77D3C691&View=%7B94C838B2%2DE166%2D4122%2DB8B4%2D7BEB9E1BC12B%7D | Katie Izenour (ICF/CDC) viq9@cdc.gov Katya Noykhovich (Peace Corps) knoykhovich@peacecorps.gov Kimi Sato (Peace Corps) ksato@peacecorps.gov Shazad Ahmed (ICF/CDC) lqa9@cdc.gov
DRC | 05/2017 | TDY to Field | 11/27/2017 - 12/7/2017 |  | Jamie Houston | Capacitate DRC staff on DRC MER tool, ICPI data and tools; provide training/support on using FactView | Approved | 1917-10-01 | Shazad Ahmed, Noah Bartlett, JP Abellera | Shazad Ahmed | Completed | TDY completed - trainings were held and were successful. Jacob sent a follow up email to leads and POCs. | At this point, the next steps are to incorporate final requests into the DRC MER tool, update the tool with 'cleaned' Q4 data and then generate document on how to update the tool. | 1. Submit final draft of tool by 12/21 2. Update tool with cleaned Q4 data by mid january |  | https://www.pepfar.net/OGAC-HQ/icpi/Shared%20Documents/ICPI%20Work%20Products%20Library/Broad%20Engagement/Country%20Engagement/drc%20tool%20draft%20113017.xlsx | Shazad Ahmed (CDC/ICF) lqa9@cdc.gov Noah Bartlett (USAID) nbartlett@usaid.gov JP Abellera (CDC) jla7@cdc.gov
Ethiopia | 05/2017 | Virtual Support | N/A | Sisay Abayneh | Bob Gern | Integrated Dashboard for IP monitoring | Approved | 2017-05-16 | Katie I, Shazad, Imran, and Ray S | Jamie Houston | Ongoing | Dashboard created and presented to leads in mid-July but pulled from ICPI clearance, being used by CDC Ethiopia and MOH in Ethiopia, agreement on need for interagncy | HQ POCs working to resolve interagency concerns and determine next steps (likley requires side meeitng in Joburg to resolve) |  |  |  | Katie Izenour (ICF/CDC) viq9@cdc.gov Shazad Ahmed (ICF/CDC) lqa9@cdc.gov Imran Mujawar (ICF/CDC) lrz5@cdc.gov
DRC | 02/2017 | TDY to Field | 04/11/2017 - 04/20/2017 | Jacob Dee | Bob Gern | Integrated Dashboard for IP monitoring | Approved | April? | Shazad (TA from Aaron/Noah as needed) | Shazad Ahmed | Completed | TDY to DRC 2 weeks in April, Draft tool reviewed by HQ POCs in May. Multiple iterations of tool shared. | Follow up TDY completed, see see 05/2017 request for more details | 2017-11-17 |  | https://www.pepfar.net/OGAC-HQ/icpi/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FOGAC%2DHQ%2Ficpi%2FShared%20Documents%2FICPI%20Engagement%2FDemocratic%20Republic%20of%20the%20Congo&FolderCTID=0x012000C815322C717A7E4B8164EA374FA254EC002682B939F9BED347BD49E43D77D3C691&View=%7B94C838B2%2DE166%2D4122%2DB8B4%2D7BEB9E1BC12B%7D&InitialTabId=Ribbon%2ERead&VisibilityContext=WSSTabPersistence | Shazad Ahmed (CDC/ICF) lqa9@cdc.gov Noah Bartlett (USAID) nbartlett@usaid.gov Aaron Chaffetz (USAID) achaffetz@usaid.gov
South Africa | 01/2016 | Virtual Support | 02/2016 10/2016 04/2016 | Amy Herman Roloff (CDC South Africa) | Bob? Travis? | District Profiles Dashboard support; Data management, process automation, visualization, data integration | Referred/ CDC-specific request |  | Abe, Travis, JP | JP Abellera | Transferred | Presented at PALS by Sarah, interagency meeting to discuss transition plan to field to update dashboard. Phase II complete, phase III update and transition is ongoing. | To CDC HQ, Sarah and Ambereen to determine next steps for interagency collaboration Dana Greeson (CDC SA contractor) to update with Q3 clean data and multiple other updates | N/A, in process no specific deadline but as availability allows |  | pfip-sa.data.socrata.com | Abe Agedew (ICF/CDC) lqe1@cdc.gov JP Abellera (ICF/CDC) jla7@cdc.gov

## Visitors to ICPI HQ
ICPI Visitor Log
Objective: | This log documents visitors to ICPI's main office in Washington, DC to better track visitors and agency involvement.
Last updated: | 2018-01-09
By: | Kashmira Kale
Contact: | ICPI@state.gov
Name | Agency | Filled out ICPI Engagement Form? | Type of Visit | Interagency? Agency-Specific? | Start Date | End Date
Ramona Bhatia | CDC | No | ICPI Pre-Deployment | CDC-specific | 1/4/18 | 1/5/18
Pam Bachanas | CDC | No | ICPI Pre-Deployment | CDC-specific | 1/4/18 | 1/5/18
Erin Rottinghaus | CDC | No |  |  | 2017-11-07
Kimberly Boer | CDC | No | Training | CDC-specific | 2017-11-06 | 2017-11-06
Lisa Esapa | CDC | No | ICPI Pre-Deployment | CDC-specific | 2017-11-06 | 2017-11-07
Don Sharman | CDC | No | ICPI Pre-Deployment | CDC-specific | 2017-11-06 | 2017-11-07
Kathleen Jacobson | CDC | No | ICPI Pre-Deployment | CDC-specific | 2017-11-06 | 2017-11-07
Subomi Adeyemo | CDC | No | ICPI Pre-Deployment | CDC-specific | 2017-11-06 | 2017-11-06
Mike Melchior | CDC | No |  |  | 2017-10-31
Stephanie Hess | DoD | Yes | Training | Interagency | 2017-10-30 | 2017-11-02
Audrey Knutson | CDC | No | Training | Interagency | 2017-10-30 | 2017-11-03
Val Reagon | CDC | No | Training |  | 2017-10-30 | 2017-11-02
Biesse Soura | CDC | No | Training |  | 2017-10-30 | 2017-11-02
Barbara Ddamulira | DoD | No | Webinar | Interagency | 2017-11-13 | 2017-11-13
Mike Melchior | CDC | No |  | Interagency | 2017-11-13
Christine Fu | USAID | No | Training | Interagency | 2017-11-07 | 2017-11-07
Amy Aberra | USAID | No | Training | Interagency | 2017-11-07 | 2017-11-07
Christine Fu | USAID | No | Training | Interagency | 2017-10-30 | 2017-11-02
Amy Aberra | USAID | No | Training | Interagency | 2017-10-30 | 2017-11-03